## Sheet1
Product Backlog ID | User Story Task Step Number | Task Step Description | Assigned Date | Original Estimate | Adjustment Estimate | Status | Actual Effort
PECUNIABANK_01 | 1 | Test case Template | 2020-08-03 | 1.5 hrs |  | Completed
| 2 | Product Backlog | 2020-08-03 | 1 hr |  | Completed
| 3 | Sprint Plan Sheet | 2020-08-03 | 1 hr
| 4 | Entity Class Design |  | 2 hrs
| 5 | Use Case Diagram |  | 1.5 hrs
| 6 | Sequence Diagram |  | 1.5 hrs
PECUNIABANK_02 | 1 | Creating a Spring boot starter project |  | .5hr | .5hr
| 2 | Adding dependencies in Pom.xml and initializing it |  | 1 hr | 1hr
| 3 | Adding server, jpa and logging properties in application.properties |  | 1 hr | 1hrs
PECUNIABANK_03 | 1 | CREDIT TRANSACTIONS; DAO |  | 3 hrs | 0.5 hrs
| 2 | CREDIT TRANSACTIONS; SERVICE |  | 3 hrs | 0,5 hrs
| 3 | CREDIT TRANSACTIONS; CONTROLLER |  | 3 hrs | 0,5 hrs
PECUNIABANK_04 | 1 | Populating the test data in database |  | 3 hr | 0.5 hrs
PECUNIABANK_05 | 1 | Testing the functionalites in postman |  | 3 hrs | 1hr